## Coverpage
National Accreditation Board for
Hospitals and Healthcare Providers
Sample Template for Project Plan for EMR Implemention

## Project Plan
Project Plan
Vendor Name
Product Name
Project Manager(s)
Contact Details
Email Address
Sl. No. | Task Name | Task Owner | Start Date | End Date | Status
A | Project Details
1 | Define project scope / SoW | Hospital
2 | Complete vendor information forms or due diligence forms | Hospital
3 | Evaluate server type and configuration - on-prim vs cloud | Hospital
4 | Finalize server configuration and handover to vendor | Hospital
5 | Complete data collection forms, due diligence or any other documentation | Hospital
6 | Identify key stakeholders, project champions and assign responsibilities | Hospital
7 | Review & finalize various departmental workflows | Vendor / Hospital
B | Project Setup
1 | Setup servers, create instance, hospital account, assign team | Vendor
2 | Collect data from all the masters as applicable in the required format | Vendor
- Create your own list for all the item masters like Pharmacy, Blood Bank, Organization Structure, Employees, Patients, Vendors, Rate Sheets, etc. as applicable
3 | Data configuration for all the masters to the new system | Vendor
4 | Setup various modules as per the agreement | Vendor
- Create your own list as per the requirements. Example: Appointment management, Registration, Nursing, OT, Lab, Radiology, Inventory, Linen, Billing, Insurance, Protocol, etc.
5 | HIS/EMR Setup - IPD Module, OPD Module etc. | Vendor
6 | Verify HIS/EMR flow, templates, formats | Vendor
7 | Demostration of the application and its workflows to the project champions | Vendor
C | Integrations
1 | Integration with Third-party Applications & devices (as applicable) | Vendor
2 | Configurations of barcode printers, printers, etc. | Vendor
3 | Teleconsultations / TeleICU platforms (if applicable) | Vendor
4 | ABDM - M1, M2 and M3 compliance (hospital system) | Vendor
5 | Provider integrations like PMJAY, etc. | Vendor
6 | WhatsApp integration | Vendor
7 | Any other thrid party integration (specify the application & vendor name) | Vendor
D | Data Migration
1 | Identify and list all the data to be migrated to new system | Hospital
2 | Share the existing database schema with the vendor | Hospital
3 | Vendor to share the formats required for data export | Vendor
4 | Share the legacy data with the vendor in the required format | Hospital
5 | Mapping legacy data to new database fields | Vendor
6 | Data transfer to the new system | Vendor
7 | Testing and verification of legacy data | Vendor
8 | Testing and verification of new data inputs | Vendor
E | Testing / UAT
1 | User Testing by champion users | Hospital
2 | Business workflow testing by the end users | Hospital
3 | User Acceptance Testing (UAT) with key stakeholders | Hospital
4 | Performance testing by the IT team | Hospital
F | Training
1 | Analyse and document the complete training needs | Vendor
2 | Create training schedules/batches for all the modules & user groups | Vendor/Hospital
3 | Identify super users / champions | Hospital
4 | Train the project champions / super users | Vendor
5 | Create the feedback machnesim for reporting bugs/issues | Vendor
G | Go-Live
1 | User creations and role mapping is completed | Vendor
2 | Data backup processess setup and tested | Vendor
3 | Disaster recovery or business continuity plan setup and tested | Vendor
4 | Security & data privacy is in place (2FA, IP restrictions, password poilicy, etc.) | Vendor
5 | Go-live & celebrate | Vendor