## Coverpage
National Accreditation Board for
Hospitals and Healthcare Providers
NABH HIS/EMR Go Live Checklist

## Go live Checklist
Go Live Checklist
Sl. No. | Task Name | Task Owner | Accountability | Date | Status
1 | Plan and identify one department for go-live | Hospital | Hospital
2 | Ensure the EMR system complaince with the defined workflow | Vendor/Hospital | Hospital
3 | Superusers are available to support staff during go-live | Hospital | Hospital
4 | Have vendor representatives and IT support on-site during go-live | Vendor | Vendor
5 | All the masters are uploaded and updated | Vendor | Hospital - IT Team
6 | Export master data from the new EMR system and complete data validation | Vendor | Hospital - IT Team
7 | UAT / User Acceptance Testing is completed and sign-off received from respective departments | Vendor | Hospital
8 | User creations and role mapping is completed and verified | Vendor | Hospital - IT Team
9 | Data backup processess are setup and tested | Vendor | Hospital - IT Team
10 | Security & data privacy is in place (2FA, IP restrictions, password poilicy, etc.) | Vendor | Hospital - IT Team
11 | Disaster recovery or business continuity plan setup and tested | Vendor | Hospital - IT Team
12 | Monitor system performance and nsure they match with agreed SLAs | Vendor | Hospital - IT Team
13 | Executive approval to go-live is receved | Hospital | Hospital
14 | Go-live & celebrate | Vendor | Hospital