## Slide 1: Theme: Digital Engagement Adoption Name of the Initiative : Digitalization of kits using Technology Inventory Management Application-Anytrac
Department: OT Pharmacy
Initiative Start Month: October’24
Ongoing
Mentor and Guide: Mr. Kushagra Vashishth| Chief-Non Clinical Operations
Leadership: Mr. Diju Nair |Pharmacy

## Slide 2: Key Operational Challenge/Problem?
Manual preparation of kits
Location of both the departments
Quality Issue:
1. Unhygienic conditions while transfer- dust on crates etc as well as
2. Inventory getting damage while transfers.
Patient Safety Issue :
1. Inability to trace the culprit batch, in case of ADRs.
2. Cold Chain non compliance
3. Potential chances of dispensing errors.
Turn Around Time > 24 hours.

## Slide 3: Gap Analysis- OT Nursing
Patient Safety
Place
Kits prepared in Basement Pharmacy and Transferred to 8th Floor OT
Lack of awareness of the importance of maintaining cold chain compliance
No kits reconciliation
People
Process
No Maker Checker Process
Manual preparation of kits
Resources
No Chiller Boxes while transit
Damaged Inventory
Cold Chain Non Compliance
TAT > 24 hrs

## Slide 4
Plan
Team role and Responsibilities
Designation
Roles
Senior Pharmacist
ZMRP
Inventory Isolation
Junior Pharmacist
Re-Engineering layout
Color Coded crates
Executive Pharmacist
Commercial Fridge
Steel Stand
Assistant Manager Pharmacy
Cold Chain Compliance
Group ID Creation
SPOC Senior Manager-Pharmacy
Template Separation
Training MIS
SPOC Nursing Manager
Team Alignment
Ground level Implementation
Scope | OT Kit Preparation
Location | 7th and 8th Floor
Team | Nursing Technicians
Exceptions | Emergency, Addons
Time Period | At least 6 months
Initial Target | Nursing
Team Strength | 70-80 Nos.
Template Count | 140
Go Live | 6 months
Staff Training | TLs
Train the Trainer | 5 nurses/TL
Small Teams | Refresher Training
Hands on Training | IT
On site Support | IT
Designation | Roles
Senior Pharmacist | ZMRP Inventory Isolation
Junior Pharmacist | Re-Engineering layout Color Coded crates
Executive Pharmacist | Commercial Fridge Steel Stand
Assistant Manager Pharmacy | Cold Chain Compliance Group ID Creation
SPOC Senior Manager-Pharmacy | Template Separation Training MIS
SPOC Nursing Manager | Team Alignment Ground level Implementation

## Slide 5: Digital Solution : Anytrac Application
Aim : Digitalization of Transactions Via Scanning Inventory
Path: Start Small and Grow big
Cross Functional Teams
Scope: Long Stay Procedures.
Set Accountability : Identify TLs and “Train the Trainer” concept.
Method: The 3 Rules
Gemba Walk
Insights, feedbacks and suggestions from OT Teams.
Monitor daily count of specific cases and transactions.
Scale up to expand all specialties cases.

## Slide 6: Anytrac –Digital Tool
Developed Inhouse and WIFI support.
Process Walks
High transmission Speed and easy to use hand held devices.
Integration of SAP
Customized and related updating.
User friendly.
Team IT 24*7 support
Dashboard and KPI Reporting

## Slide 7: Anytrac Application-Process Flow
Start
Reservation Pending
Material Issued
Inward
Consumption Marked
Balance Auto returned
Returns Accepted
Transaction Completed
Reservation Raised
End
QR Code Scan
Batch wise scan

## Slide 8: Action Plan
SN | Problem | Solution | Plan
1 | Incomplete kits | Digitalization | Digitalize using Anytrac Application all planned cases except emergency
2 | Kit Handover TAT > 24 hrs | Material Replenishment process to be digitalization using SAP. Inventory correction (Mar’24) | Isolation of high value inventory ZMRP ROL-MIN-MAX to be set and Push Method Inventory Split Batch correction
 |  | Counselling and Teams to be split setting inventory accountability Kit handover TAT tracker to be introduced | Split the Pharmacists team handling Consumable and Drugs
 |  | Layout /Re-engineering to be done for efficient storage. | Location to be defined for back up and planned cases kit, labeled and isolated with access to authorized personnel.
3 | Unorganized way of preparing kits and handling materials. | Additional small crates to be planned Education session to be planned, intra and inter departmentally | Color Coded Crates Training MIS
4 | Kit Handover TAT > 8 hours | Inventory categorization in app | Oct’24 -139 Nursing and Technician side kits were split.

## Slide 9: Action Plan
SN | Problem | Solution | Plan
5 | Communication | Exclusive channel of communication needs to be established | Group ID to be created and 24*7 On call Number
6 | Transaction Incompleteness | Stakeholders to be informed in 24 hrs post procedure for closure. | Take access of Surgery portal report and inform for transaction incompleteness
Quality Compliance
Steel Stands | Commercial Fridge |Chiller Boxes

## Slide 10: Results- Anytrac Compliance-Nursing Side Path
Chart: 
| 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931
Anytrac Vs Planned Cases(%) | 0.55345 | 0.55431 | 0.67691 | 0.53093 | 0.64454 | 0.40543 | 0.4 | 0.33145 | 0.61224 | 0.39451 | 0.07874 | 0.36071 | 0.39163
% Compliance | 0.7163 | 0.75152 | 0.91933 | 0.90254 | 0.97033 | 0.97368 | 0.91667 | 0.97952 | 0.94444 | 0.85851 | 0.97143 | 0.91354 | 0.88994
1.ZMRP Autorun
2. Base stand
3.Commerical grade fridge
Re-Engineered Layout
Chiller Boxes
Training MIS
Surgery Portal report access
Chiller Boxes
On call Phone
% Compliance has increased from 72 to 89 in a year

## Slide 11: Anytrac Compliance- Nursing Side Kits (Apr’25 till Mar’26)
Chart: % transaction completeness
| Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov'25 | Dec'25 | Jan'26 | Feb'26 | Mar'26
% Compliance | 0.91667 | 1 | 0.94444 | 0.85851 | 0.97143 | 0.91354 | 0.88994 | 0.97436 | 0.92823 | 0.95992 | 0.98867 | 0.9

## Slide 12: Dashboard

## Slide 13: Expand Technicians and Perfusionists Start Month:Oct’25 End Month: Dec’25

## Slide 14
Plan
Team role and responsibilities
Scope | OT Kit Preparation
Location | 7th and 8th Floor
Team | Technicians
Exceptions | Emergency, Addons
Time Period | At least 6 months
Initial Target | Technicians
Team Strength | 30 Nos.
Process | Direct Charging
Go Live | 3-6 months
Staff Training | Leads
Train the Trainer | 10/TL
Small Teams | Refresher Training
Hands on Training | IT
On site Support | IT
Designation | Roles
Senior Pharmacist | ZMRP Inventory Isolation
Junior Pharmacist | Re-Engineering layout Color Coded crates
Executive Pharmacist | Commercial Fridge Steel Stand
Assistant Manager Pharmacy | Cold Chain Compliance Group ID Creation
SPOC Senior Manager-Pharmacy | Template Separation Training MIS
SPOC Lead Technician(2 Nos.) | Team Alignment Ground level Implementation

## Slide 15: Anytrac Compliance-Technician Side Path
Technician Side Kits :Allowed Re-initiation of Scanning using existing process
Technician Side |  |  |  |  |  | 
Month | SKUs | Quantity | Amount( in lacs) | Patient Count | % Coverage | Total Cases
Oct'25 | 82 | 101 | 0.07 | 35 | 4% | 812
Nov'25 | 3,926 | 8,662 | 6.42 | 296 | 31% | 888
Dec'25 | 12,599 | 32,131 | 24.03 | 757 | 85% | 958
Jan'26 | 13,457 | 29,385 | 21.46 | 798 | 89% | 901
Feb'26 | 11,621 | 23,844 | 14.41 | 731 | 80% | 918
Mar'26 | 11,978 | 23,168 | 15 | 768 | 78% | 981
Apr'26 | 13,062 | 32,338 | 17.62 | 835 | 85% | 984
Perfusionists Side Kits : Pharmacists Proactively Initiated
Perfusionist Side Kits |  |  |  | 
Month | SKUs | Quantity | Amount( in lacs) | Patient Count
Oct'25 | 175 | 280 | 0.31 | 45
Nov'25 | 210 | 379 | 0.31 | 48
Dec'25 | 350 | 968 | 0.91 | 39
Jan'26 | 198 | 304 | 1.34 | 42
Feb'26 | 1271 | 2365 | 4.03 | 41
Mar'26 | 1902 | 6169 | 7.11 | 57
Apr'26 | 1420 | 4751 | 2.73 | 47

## Slide 16: Operational and Cost Efficiency
SN | Impact | Pre Digitalization | Post Digitalization
1 | Daily Manual Requirements | 100% Manual | Nurses -40% Technicians- 85% Perfusionists – 100%
2 | Digitalization | 24 hours | 8 hours
3 | Process Efficiency cases/day | Zero | Nurses and Technicians-30 to 35 Perfusionists- 2-3
4 | Dispensing Errors | Incompleteness -50% of cases | Zero ( Not a single CQI)
5 | Inventory Coverage Medicines/Month/800 cases | Zero | Nurses --10K-11K Technicans-30K Perfusionists-4K
6 | Complaints | 50% of the kits either had incompleteness/ dispensing errors. | Reduced to 10-15%No complaints
7 | Inventory | No fixed replenishment method. Manually Based on visual replenishment/Judgement | PUSH METHOD Initiated. No Stock Outs. Block Inventory is now Zero. Tied up capital (Dead Inventory) reduced by 17% (July’25 to Dec’25)

## Slide 17: Appreciations and Awards
Feb 2026- Won Special Recognition at the RIL SPECTRUM –Annual learning Event in the Challengers League as LEARNING CHAMPIONS amongst 180 participants, 40 Champions, and 10 Finalists across the group.
Feb 2026- Re-Felicitated by our Organization for Winning the Award at the Spectrum Event
Feb 2026 – Won the WOW award for driving 100% compliance using the application mirroring the success achieved with nursing kits to Technicians and Perfusionist
Recognized for Outstanding teamwork, innovation, and commitment to operational excellence

## Slide 18: Appreciations and Awards
January 2025-
Won the WOW Award for displaying CORE VALUE –”PATIENT FIRST”

## Slide 19: Replicate Cath Lab Start Month: Mar’26 Ongoing

## Slide 20: Gap Analysis-Cath Lab
Place
People
Process
Patient Safety
No fixed location for storing planned kits template
Manual preparation of kits
No Maker Checker Process
Medicine duplication in templates
No kits reconciliation
Unaccounted medicines left in labs
Cut strip practice
Resources
No near expiry checks
Lack of secure storage of high cost medicines
No Refrigerator
No back up kits
Single kit used on two patients
Incomplete kits

## Slide 21
Plan
Team role and Responsibilities
Scope | Cath Lab Kit Preparation
Location | 7th Floor
Team | Nursing
Exceptions | Emergency, Addons
Time Period | At least 3 months
Initial Target | 100% Planned cases
Team Strength | 10 nurses
Template Count | 24
Go Live | 3 months
Staff Training | IT
On site Support | IT
Process | Via Procedure Templates
Designation | Roles
Assistant Manager Pharmacy | Cold Chain Compliance Code Mapping in 24 case template Random Audits Back up kits readiness
Executive Pharmacist | Material replenishment Pilot case support Kit preparation and handover Storage Compliance
Manager-Nursing | Alignment of Refrigerator Finalizing the kit requirements Fixing responsibilities Alignment of Manpower Arranging Resources
Team IT –Two Members | Team Training Template mapping in application Pilot case support Solving Go-Live queries

## Slide 22
Action Plan
SN | Problem | Solution | Implementation Steps | Timeline | Responsible Person
1 | No Refrigerator | Either a Refrigerator to be arranged/ existing refrigerator of PACU unit to be used. | Existing Refrigerator of PACU is utilized | 25th Mar’26 | Manager Cath Lab
2 | Cut strip practice | Regularly used tablets to be either included as a part of PTCA kit / to be maintained in Cath Lab SLOC and charged to the patient as whole | Separate template of all ten brands of tablets is created. One template to be maintained in Cath SLOC for emergency use and will be charged from SLOC. Replenishment will be provided by Main Store. Any requirement over an above will be given from OT pharmacy and charged to the patient same time | 7th April’26 | Manager Cath Lab and Pharmacist
3 | Single kit used on two patients | Team to be briefed to stop the practice of picking medicines from kits inside the OT. Anesthesia drug templates maintained inside each lab to be reviewed for additions to avoid dependency on kits. | Team is briefed not to use /pick up drugs randomly from kits for use in case. Real time kit checking and return kits practice to be started at both levels –Cath Lab and OT Pharmacy | 31st Mar’26 | Manager Cath Lab and Pharmacist
4 | Medicine duplication in templates | Existing Three Templates – Supra Major/ GA Major and Anesthesia side drugs to be reviewed an merged into one single template to be maintained in each lab | One single kit-Anesthesia drugs is finalized containing 125 drugs and consumables. Random audit is performed to check physical stocks | 1st April’26 4th April 26 & 11th April’26 | Manager Cath Lab and Pharmacist

## Slide 23
Action Plan
SN | Problem | Solution | Implementation Steps | Timeline | Responsible Person
5 | No near expiry checks | To fix a frequency amongst Cath Lab on duty team to check near expiry and isolate stocks. | Weekly near expiry check practice is reinforced on the Cath Lab team with a cut off date being month end. Accountability fixed on the on duty Coordinator | 26th Mar’26 | Manager Cath Lab and Pharmacist
6 | Unaccounted medicines left in labs | Team to be briefed to discard partly used vials and not leave them scattered on the equipment. Initiation of back up kits in each lab will stop this practice | All the stocks lying in Cath Lab are to be returned back to OT Pharmacy and the revised Anesthesia drug kit will be issued manually for each lab | 1st April’26 | Manager Cath Lab
7 | No kits reconciliation | Identify Back up kits to be maintained in each lab. Anesthesia side kits to be maintained in each lab for use in case. Planned cases requirements to be raised separately. Replacements of back up kits will be provided by Pharmacy same time. | Real time kit checking to be started in both Cath Lab and OT Pharmacy and discrepancy to be highlighted same time. | 1st April’26 | Manager Cath Lab and Pharmacist

## Slide 24
Action Plan
SN | Problem | Solution | Implementation Steps | Timeline | Responsible Person
8 | Manual preparation of kits | Anytrac Application use to be explored to fasten up the process. | 1. Material code to be mapped in 24 templates 2. Staff Training 3. Pilot case | 25th April’26 6th May’26 6th May’26 | Pharmacist IT Team Manager Cath Lab ,Pharmacist and Team IT
9 | No Maker Checker Process |  |  |  | 
10 | Incomplete kits |  |  |  | 
11 | No back up kits | Define the count and procedures to be maintained in Cath lab and OT Pharmacy | Three PTCA kits to be maintained in Cath lab. One Embolization and Mechanical Thrombectomy kit to be maintained as Emergency kit in OT Pharmacy | 7th April ’26 | Manager Cath Lab and Pharmacist
12 | No fixed location for storing planned cases | Location to be defined to maintain back up kits, Anesthesia side drugs. Planned drug kits to be maintained separately to avoid mix up. | Team is briefed to keep two PTCA kits in Lab 1 and one PTCA in Lab 2. Planned case templates to be stored in CU Store area only. Upon usage | 28th April’26 | Manager Cath Lab
13 | Lack of secure storage of high cost medicines | Lockers to be made/pedestal to be placed under the camera surveillance. | Oral tablets to be maintained in the pedestal- access to be given to the coordinator and a register to be initiated to record usage and replenishment details. | 5th April’26 | Manager Cath Lab and Pharmacist

## Slide 25: Operational Efficiency
SN | Impact | Pre Digitalization | Post Digitalized
1 | Daily Planned cases | Manually | 100 % planned cases
2 | Kit Handover TAT | 24 hours | 8 hours Kit Preparation Time shifted from Night to Day Shift. On duty Pharmacists and Cath Lab can work efficiently in department related tasks and other activities.
3 | Inventory Batch Mismatch | All mismatch | 100% match
4 | Output/Month | Manually | 279 medicines/350 Quantity/60 cases
5 | Inventory/ Work Duplication/Transaction Duplication | Three Templates contain 107 medicines. | Reduced to 70% due to template uniqueness. merged to a single template -76 medicines
6 | Incomplete kits/day | 3-4 cases | Zero. Staff moving steps reduced in day shift during peak hours.
Month | SKUs | Quantity | Amount( Rs.) | Patient Count
May'26 | 279 | 349 | 16,000 | 59

## Slide 26: Scale up Floor 12th LR OT Start Month: June’26 Ongoing

## Slide 27: Gap Analysis
People
Process
Patient Safety
Manual preparation of kits
No Maker Checker Process
Material
Batch mismatch due to manual charging
Technician side medicines being used from kits/ward stocks
Excess and Shortages in kit stock
Insufficient/ Excess Ward stocks

## Slide 28
Plan
Team role and Responsibilities
Designation
Roles
Senior Pharmacist
ZMRP
Inventory Isolation
Junior Pharmacist
Re-Engineering layout
Color Coded crates
Executive Pharmacist
Commercial Fridge
Steel Stand
Assistant Manager Pharmacy
Cold Chain Compliance
Group ID Creation
SPOC Senior Manager-Pharmacy
Template Separation
Training MIS
SPOC Nursing Manager
Team Alignment
Ground level Implementation
Scope | Labour OT
Location | 12th Floor Floor
Team | Nursing
Exceptions | Emergency, Addons
Time Period | One month
Initial Target | Planned cases
Team Strength | 10 nurses.
Template Count | 5
Go Live | One month
Staff Training | All nurses
Small Teams | Refresher Training
Hands on Training | IT
On site Support | IT
Designation | Roles
SPOC Assistant Manager-Pharmacy | Template Separation Stock arrangement
SPOC Nursing Manager | Team Alignment Ground level Implementation Review Ward stocks post Go-Live

## Slide 29: Action Plan
SN | Problem | Solution | Implementation Steps | Timeline | Responsible Person
1 | Insufficient /Excess ward stocks | Based upon the medicines required in kit , rest can be kept in ward stock | Review the existing templates based on the requirements in cases and the need to pick up stocks of ward issue. Map the ward specific materials in kits | 15th June | Nursing
2 | Manual kit preparation | Anytrac Implementation | To start with one planned case on pilot basis and scale up | 10th June | Nursing-Pharmacist
3 | Excess and Shortages | Anytrac Implementation | To match the physical stocks Vs ward stock items. Post Anytrac Implementation, review the ward stock items and remove the slow/non moving retaining critical materials. | One month after successful implementation | Nursing
4 | Batch mismatch | Anytrac Implementation | To start with one planned case on pilot basis and scale up | 10th June | Nursing-Pharmacy
5 | Technician side medicines being used from kits/ward stocks | Restricted access and use only to nursing side | Restrict access of technicians to use ward stocks. Technicians need to place their kits prior the case. In case of additional requirements, can the ward materials be used. | Immediate | Nursing-Technicians

## Slide 30: …Thank you…